## Financial progress
Sr. No. | Financial progress parameters
1 | Name of the work
2 | Name of the contractor
3 | Estimated tender cost
4 | Approved tender cost
5 | No. of bidders who submitted the bid
6 | Tender sanctioning authority
7 | Tender sanctioned vide resolution no.___ dated ___
8 | Time period to complete the work
9 | User department
10 | Account code
11 | Sanctioned budget amount
12 | Project code
13 | Letter of Intent date
14 | Work order date
15 | Anticipated date of completion
16 | Bank guarantee amount and validity
17 | Mobilization advance paid, if any
18 | Mobilization advance recovered, if any
19 | Outstandin mobilization amount
20 | Bank guarantee details submitted against mobilization advance
21 | Status on recovery of mobilization advance
22 | Extension of time limit given (Authority's resolution no. and period till which it is extended)
23 | Revised tender cost and resolution no.
24 | Total amount of work done (to be updated on fixed intervals)
25 | Total amount withheld from the bill (retention money, material testing charges, penalty etc.)
26 | Total amount paid till date to the contractor
27 | Value of outstanding liabilities (work certified but unpaid)
28 | Extra items (amount and resolution no.)
29 | Financial progress in a graphical presentation
30 | Milestone achievement
31 | Penalty amounts, if any
32 | Comparative statement approval
33 | Name of the Project Management Consultant
34 | Estimated fees for consultancy
35 | Work completion date
36 | Defect liability period
37 | Performance bond (amount & validity)
38 | RA bill wise financial progress (Work period & amount of work done)

## Sheet4
Sr | Name of the work | Name of the contractor | Estimated tender cost (₹ Cr) | Approved tender cost (₹ Cr) | No. of bidders | Tender sanctioning authority | Tender sanctioned vide resolution no. | Tender sanctioned vide resolution dated | Time period to complete the work | User department | Account code | Sanctioned budget amount (₹ Cr) | Project code | Letter of Intent date | Work order date | Anticipated date of completion | Bank guarantee amount (₹ Cr) | Bank guarantee validity | Mobilization advance paid (₹ Cr) | Mobilization advance recovered (₹ Cr) | Outstanding mobilization amount (₹ Cr) | BG details against mobilization advance | Status on recovery | Extension resolution no. | Extension period upto | Revised tender cost (₹ Cr) | Revised tender resolution no. | Total work done (₹ Cr) | Amount withheld (₹ Cr) | Total paid till date (₹ Cr) | Outstanding liabilities (₹ Cr) | Extra items amount (₹ Cr) | Extra items resolution no. | Financial progress | Milestone achievement | Penalty amount (₹ Cr) | Comparative statement approval | PMC name | Consultancy fees (₹ Cr) | Work completion date | Defect liability period | Performance bond amount (₹ Cr) | Performance bond validity | RA bill work period | RA bill amount (₹ Cr)
1 | Road Widening | ABC Infra | 25 | 24.5 | 5 | PWD | 101/2023 | 2023-01-15 | 18 Months | PWD | AC001 | 26 | PRJ001 | 2023-02-01 | 2023-02-15 | 2024-08-14 | 2.45 | 2025-08-31 | 2 | 1.2 | 0.8 | Submitted | Ongoing |  |  |  |  | 15 | 0.75 | 13 | 2 |  |  | 60% | Phase-2 completed | 0.1 | Approved | XYZ PMC | 0.8 | 2024-07-30 | 12 Months | 2.45 | 2025-08-31 | Feb–Jun 2024 | 5
2 | Water Supply Scheme | DEF Projects | 18 | 17.2 | 4 | Municipal Corp | 102/2023 | 2023-02-28 | 12 Months | Water Dept | AC002 | 18.5 | PRJ002 | 2023-03-10 | 2023-03-25 | 2024-03-24 | 1.72 | 2025-03-31 | 1.5 | 1 | 0.5 | Submitted | Partial |  |  |  |  | 12.5 | 0.6 | 11 | 1.5 | 0.5 | 210/2023 | 70% | Phase-3 completed |  | Approved | ABC PMC | 0.6 | 2024-03-15 | 12 Months | 1.72 | 2025-03-31 | Apr–Dec 2023 | 12.5
3 | Bridge Construction | GHI Builders | 40 | 38.75 | 6 | State Govt | 110/2023 | 2023-01-05 | 24 Months | PWD | AC003 | 42 | PRJ003 | 2023-01-05 | 2023-01-20 | 2025-01-19 | 3.88 | 2026-01-31 | 3 | 1.5 | 1.5 | Submitted | Ongoing | 205/2024 | 2025-06-30 | 41 | 205/2024 | 20 | 1.2 | 18 | 2 | 1.25 | 215/2024 | 52% | Pier work completed | 0.25 | Approved | Infra PMC | 1.2 | 2025-06-30 | 24 Months | 3.88 | 2026-01-31 | Jan–Dec 2024 | 20
4 | Govt Office Building | JKL Engineers | 12 | 11.5 | 3 | Urban Dev Dept | 115/2023 | 2023-03-20 | 15 Months | UD Dept | AC004 | 12.5 | PRJ004 | 2023-04-01 | 2023-04-20 | 2024-07-19 | 1.15 | 2025-07-31 | 1 | 0.7 | 0.3 | Submitted | Ongoing |  |  |  |  | 8 | 0.4 | 7 | 1 |  |  | 65% | Structure completed |  | Approved | Build PMC | 0.45 | 2024-07-15 | 12 Months | 1.15 | 2025-07-31 | May 2023–Jan 2024 | 8
5 | Drainage Network | MNO Construction | 9 | 8.75 | 4 | Municipal Corp | 118/2023 | 2023-04-10 | 10 Months | Drain Dept | AC005 | 9.5 | PRJ005 | 2023-05-12 | 2023-06-01 | 2024-03-31 | 0.88 | 2025-03-31 | 0.7 | 0.5 | 0.2 | Submitted | Ongoing |  |  |  |  | 6 | 0.3 | 5.5 | 0.5 |  |  | 68% | Section-A completed |  | Approved | City PMC | 0.3 | 2024-03-25 | 12 Months | 0.88 | 2025-03-31 | Jun 2023–Feb 2024 | 6
6 | School Building | PQR Infra | 6.5 | 6.2 | 3 | Education Dept | 120/2023 | 2023-06-18 | 12 Months | Edu Dept | AC006 | 7 | PRJ006 | 2023-06-18 | 2023-07-01 | 2024-06-30 | 0.62 | 2025-06-30 | 0.5 | 0.3 | 0.2 | Submitted | Ongoing |  |  |  |  | 4.2 | 0.2 | 3.8 | 0.4 |  |  | 67% | Slab completed |  | Approved | Edu PMC | 0.25 | 2024-06-20 | 12 Months | 0.62 | 2025-06-30 | Jul 23–Mar 24 | 4.2
7 | Hospital Renovation | STU Works | 5 | 4.8 | 4 | Health Dept | 125/2023 | 2023-07-05 | 9 Months | Health Dept | AC007 | 5.2 | PRJ007 | 2023-07-05 | 2023-07-20 | 2024-04-19 | 0.48 | 2025-04-30 | 0.4 | 0.3 | 0.1 | Submitted | Near completion |  |  |  |  | 4 | 0.2 | 3.6 | 0.4 |  |  | 83% | Interior completed |  | Approved | Health PMC | 0.2 | 2024-04-15 | 12 Months | 0.48 | 2025-04-30 | Aug 23–Feb 24 | 4
8 | Street Lighting | UVW Electricals | 3.5 | 3.3 | 4 | Municipal Corp | 130/2023 | 2023-08-10 | 6 Months | Electrical | AC008 | 3.8 | PRJ008 | 2023-08-10 | 2023-08-25 | 2024-02-24 | 0.33 | 2025-02-28 | 0.25 | 0.2 | 0.05 | Submitted | Recovered |  |  |  |  | 3 | 0.1 | 2.7 | 0.3 |  |  | 90% | Installation completed |  | Approved | Power PMC | 0.15 | 2024-02-20 | 12 Months | 0.33 | 2025-02-28 | Sep 23–Jan 24 | 3
9 | Sewage Treatment Plant | Aqua Infra | 55 | 53.5 | 6 | State Govt | 135/2023 | 2023-09-01 | 30 Months | Water Dept | AC009 | 56 | PRJ009 | 2023-09-01 | 2023-09-20 | 2026-03-19 | 5.35 | 2027-03-31 | 5 | 2 | 3 | Submitted | Ongoing |  |  |  |  | 18 | 1.5 | 16 | 2 | 2 | 245/2024 | 34% | Civil 30% |  | Approved | Aqua PMC | 1.8 | 2026-03-31 | 24 Months | 5.35 | 2027-03-31 | Oct 23–Dec 24 | 18
10 | Bus Terminal | City Infra | 22 | 21.4 | 5 | Transport Dept | 140/2023 | 2023-09-15 | 20 Months | Transport | AC010 | 23 | PRJ010 | 2023-09-15 | 2023-10-01 | 2025-05-31 | 2.14 | 2026-05-31 | 1.8 | 0.9 | 0.9 | Submitted | Ongoing |  |  |  |  | 10.5 | 0.7 | 9.5 | 1 |  |  | 49% | Foundation completed |  | Approved | Transit PMC | 0.9 | 2025-05-15 | 12 Months | 2.14 | 2026-05-31 | Oct 23–Nov 24 | 10.5
11 | Sports Complex | FitBuild Ltd | 16 | 15.25 | 4 | Sports Dept | 145/2023 | 2023-10-05 | 18 Months | Sports Dept | AC011 | 16.8 | PRJ011 | 2023-10-05 | 2023-10-20 | 2025-04-19 | 1.53 | 2026-04-30 | 1.2 | 0.6 | 0.6 | Submitted | Ongoing |  |  |  |  | 7.8 | 0.5 | 7 | 0.8 |  |  | 51% | Track base done |  | Approved | Sports PMC | 0.55 | 2025-04-10 | 12 Months | 1.53 | 2026-04-30 | Nov 23–Dec 24 | 7.8
12 | Public Toilet Block | CleanBuild | 2.8 | 2.65 | 3 | Municipal Corp | 150/2023 | 2023-11-01 | 5 Months | Sanitation | AC012 | 3 | PRJ012 | 2023-11-01 | 2023-11-15 | 2024-04-14 | 0.27 | 2025-04-30 | 0.2 | 0.15 | 0.05 | Submitted | Recovered |  |  |  |  | 2.1 | 0.08 | 1.9 | 0.2 |  |  | 75% | Civil completed |  | Approved | Clean PMC | 0.12 | 2024-04-10 | 12 Months | 0.27 | 2025-04-30 | Nov 23–Mar 24 | 2.1
13 | Smart City CCTV | Vision Tech | 7.5 | 7.1 | 5 | Smart City SPV | 155/2023 | 2023-11-20 | 8 Months | IT Dept | AC013 | 7.8 | PRJ013 | 2023-11-20 | 2023-12-05 | 2024-08-04 | 0.71 | 2025-08-31 | 0.6 | 0.4 | 0.2 | Submitted | Ongoing |  |  |  |  | 4.9 | 0.25 | 4.4 | 0.5 |  |  | 69% | Control room done |  | Approved | Tech PMC | 0.35 | 2024-08-01 | 12 Months | 0.71 | 2025-08-31 | Dec 23–Jun 24 | 4.9
14 | Storm Water Drain | Flow Infra | 11 | 10.6 | 4 | Municipal Corp | 160/2023 | 2023-12-01 | 14 Months | Drain Dept | AC014 | 11.5 | PRJ014 | 2023-12-01 | 2023-12-20 | 2025-02-19 | 1.06 | 2026-02-28 | 0.9 | 0.4 | 0.5 | Submitted | Ongoing |  |  |  |  | 5.5 | 0.3 | 5 | 0.5 |  |  | 52% | Stretch-1 completed |  | Approved | Urban PMC | 0.42 | 2025-02-10 | 12 Months | 1.06 | 2026-02-28 | Jan 24–Dec 24 | 5.5
15 | Fire Station Building | SafeBuild | 8 | 7.6 | 3 | Home Dept | 165/2023 | 2023-12-15 | 16 Months | Fire Dept | AC015 | 8.5 | PRJ015 | 2023-12-15 | 2024-01-01 | 2025-04-30 | 0.76 | 2026-04-30 | 0.6 | 0.3 | 0.3 | Submitted | Ongoing |  |  |  |  | 3.8 | 0.2 | 3.4 | 0.4 |  |  | 50% | RCC completed |  | Approved | Safety PMC | 0.38 | 2025-04-20 | 12 Months | 0.76 | 2026-04-30 | Jan 24–Nov 24 | 3.8
16 | Community Hall | Unity Infra | 4.2 | 4 | 3 | Social Welfare | 170/2024 | 2024-01-10 | 10 Months | SW Dept | AC016 | 4.5 | PRJ016 | 2024-01-10 | 2024-01-25 | 2024-11-24 | 0.4 | 2025-11-30 | 0.3 | 0.15 | 0.15 | Submitted | Ongoing |  |  |  |  | 2.2 | 0.1 | 2 | 0.2 |  |  | 55% | Brickwork done |  | Approved | Civic PMC | 0.2 | 2024-11-15 | 12 Months | 0.4 | 2025-11-30 | Feb–Sep 24 | 2.2
17 | Library Building | Knowledge Infra | 6 | 5.7 | 4 | Education Dept | 175/2024 | 2024-02-01 | 14 Months | Edu Dept | AC017 | 6.5 | PRJ017 | 2024-02-01 | 2024-02-15 | 2025-04-14 | 0.57 | 2026-04-30 | 0.45 | 0.2 | 0.25 | Submitted | Ongoing |  |  |  |  | 2.9 | 0.15 | 2.6 | 0.3 |  |  | 51% | Slab completed |  | Approved | Edu PMC | 0.28 | 2025-04-01 | 12 Months | 0.57 | 2026-04-30 | Mar–Dec 24 | 2.9
18 | Parking Plaza | ParkBuild | 14 | 13.4 | 5 | Municipal Corp | 180/2024 | 2024-02-15 | 18 Months | Parking Dept | AC018 | 15 | PRJ018 | 2024-02-15 | 2024-03-01 | 2025-08-31 | 1.34 | 2026-08-31 | 1.1 | 0.4 | 0.7 | Submitted | Ongoing |  |  |  |  | 6 | 0.4 | 5.4 | 0.6 |  |  | 45% | Basement completed |  | Approved | Traffic PMC | 0.6 | 2025-08-15 | 12 Months | 1.34 | 2026-08-31 | Mar–Dec 24 | 6
19 | Urban Park Development | GreenScape | 5.5 | 5.2 | 4 | Horticulture Dept | 185/2024 | 2024-03-01 | 9 Months | Garden Dept | AC019 | 5.8 | PRJ019 | 2024-03-01 | 2024-03-20 | 2024-12-19 | 0.52 | 2025-12-31 | 0.4 | 0.25 | 0.15 | Submitted | Ongoing |  |  |  |  | 3.4 | 0.12 | 3.1 | 0.3 |  |  | 65% | Landscaping done |  | Approved | Green PMC | 0.22 | 2024-12-10 | 12 Months | 0.52 | 2025-12-31 | Apr–Oct 24 | 3.4
20 | IT Office Renovation | Digital Infra | 3 | 2.85 | 3 | IT Dept | 190/2024 | 2024-03-10 | 6 Months | IT Dept | AC020 | 3.2 | PRJ020 | 2024-03-10 | 2024-03-25 | 2024-09-24 | 0.29 | 2025-09-30 | 0.2 | 0.15 | 0.05 | Submitted | Recovered |  |  |  |  | 2.6 | 0.08 | 2.4 | 0.2 |  |  | 88% | Interior completed |  | Approved | IT PMC | 0.15 | 2024-09-15 | 12 Months | 0.29 | 2025-09-30 | Apr–Aug 24 | 2.6