## Physical progress
Sr. No. | Physical progress parameters | Meaning / Example
1 | Name of work | Official name or title of the project.
2 | Name of contractor | Company or agency executing the work.
3 | Name of the department | Roads & Buildings, Water Supply, Electrical Dept.
4 | Project status | Not Started / In Progress / Delayed / Completed / On Hold
5 | Geographical location | Zone, Ward, Area, City.
6 | Project start date | Date on which work officially started.
7 | Project end date | Planned or actual completion date.
8 | Scheduled vs actual timeline (graphical presentation) | Comparison between planned schedule and actual progress
9 | Duration and reason for delay | 30 days delay due to monsoon rains.
10 | Project milestones | Foundation completed,Structure completed,Electrical work finished
11 | Activity/phase wise status (eg. Site preparation, foundation work, electrical installation) | Site preparation – 100%,Foundation – 90%,Electrical – 60%
12 | Status of material delivered | Pending / Partial / Fully Delivered
13 | Labor utilization, if any | Planned: 50 ¦ Actual: 40
14 | No. of equipments put to use and utilization done | JCB: 3 (80% utilized)
15 | Material consumption (Estimated use vs. actual use) | Cement – Estimated: 500 MT ¦ Actual: 540 MT
16 | Department wise constribution (eg. Civil work progress, electrical & mechanical work progress etc.) | Civil: 70%,Electrical: 50%,Mechanical: 40%
17 | Potential risks involved (eg. Weather conditions, labor strikes, supply chain delay) | Heavy rain,Labor shortage,Material delay
18 | Current issues (on-going) | Payment delay, power issue at site.
19 | Risk mitigation plans | Alternate supplier arranged.
20 | Quality inspections | Concrete strength test passed.
21 | Defect rectification | Cracks repaired, wiring corrected.
22 | Site inspections (date, time & findings) | Details of inspection visits.
23 | Safety incidents (quantum & impact) | 2 minor injuries, no fatality.
24 | Safety compliance at work site | Helmet usage, barricading, signage.
25 | Overall progress charts | Summary view of total project progress.
26 | Handover date | Date when project is handed over to AMC
27 | Environmental factors (eg. Waste management, water management, environmental clearance) | Environmental compliance during construction

## Dummy_Data_Review
Sr No | Name of Work | Contractor | Department | Project Status | Location | Start Date | End Date | Schedule vs Actual | Delay Days | Delay Reason | Milestone | Phase Name | Phase Status | Material Delivery | Planned Labour | Actual Labour | Equipment Name | Equipment Utilization | Equipment Utilization in % | Material Name | Material Estimated | Material Actual | Department | Department Contribution | Potential Risks | Current Issues | Risk Mitigation | Quality Inspection | Defect Rectification | Site Inspection | Safety Incidents | Safety Compliance | Overall Progress % | Physical Progress % | Handover Date | Environmental Factors
1 | Road Resurfacing Phase I | ABC Infra | Roads | In Progress | Zone A | 2025-01-01 | 2025-06-30 | Slight Delay | 10 | Rain | Foundation Done | Earthwork | 100% | Partial | 45 | 50 | Boiler System | 0 | 84% | Bitumen | 500 | 520 | a | 70% | Weather | Material delay | Extra supplier | Passed | Nil | 2025-03-05 | No | High | 65 | 0.65 | 2025-07-15 | Dust control
2 | Drainage Line Work | XYZ Constructions | Water Supply | Delayed | Zone B | 2025-01-10 | 2025-05-31 | Slight Delay | 25 | Utility shift | Excavation Done | Excavation | 100% | Partial | 30 | 40 | Chilling Unit | 0 | 72% | Pipes | 300 | 310 | a | 55% | Utility conflict | Pipe shortage | Alt routing | Passed | Minor | 2025-03-08 | Minor | Medium | 50 | 0.5 | 2025-07-31 | Waste mgmt
3 | AMC Office Renovation | BuildWell Ltd | Buildings | In Progress | HQ | 2025-02-05 | 2025-04-30 | On Track | 0 | No | Civil Done | Civil | 100% | Complete | 25 | 25 | Pasteurizer | 0 | 91% | Cement | 120 | 118 | a | 100% | Labor | None | Buffer staff | Passed | Nil | 2025-04-01 | No | High | 80 | 0.8 | 2025-05-10 | Noise control
4 | Street Light Installation | LightTech | Electrical | In Progress | Zone C | 2025-02-15 | 2025-06-15 | Slight Delay | 7 | Supply | Poles Installed | Poles | 100% | Partial | 20 | 25 | Homogenizer | 0 | 78% | Cable | 200 | 210 | a | 65% | Supply delay | Cable delay | Local vendor | Passed | Nil | 2025-03-20 | No | High | 60 | 0.6 | 2025-06-25 | Energy efficient
5 | Water Tank Construction | AquaBuild | Water Supply | Delayed | Zone D | 2024-12-01 | 2025-03-31 | Slight Delay | 40 | Monsoon | Foundation Done | Foundation | 100% | Partial | 35 | 45 | Cream Separator | 0 | 69% | Steel | 80 | 90 | a | 40% | Weather | Water logging | Dewatering | Failed once | Crack fixed | 2025-02-18 | Minor | Medium | 45 | 0.45 | 2025-05-31 | Water reuse
6 | Footpath Development | UrbanWorks | Roads | In Progress | Zone A | 2025-03-01 | 2025-07-31 | On Track | 0 | No | Kerbing Done | Kerb | 100% | Partial | 28 | 30 | Storage Tank A | 0 | 88% | Tiles | 600 | 590 | a | 60% | Traffic | None | Night work | Passed | Nil | 2025-04-10 | No | High | 58 | 0.58 | 2025-08-10 | Waste reuse
7 | Storm Water Drain | DrainTech | Water Supply | In Progress | Zone E | 2025-01-20 | 2025-06-30 | On Track | 0 | No | Channel Done | Excavation | 55% | Complete | 40 | 40 | Storage Tank B | 0 | 81% | RCC | 400 | 395 | a | 70% | Flooding | None | Temp diversion | Passed | Nil | 2025-03-22 | No | High | 72 | 0.72 | 2025-07-10 | Silt control
8 | Public Toilet Block | CleanCity | Sanitation | Delayed | Zone F | 2024-12-10 | 2025-02-28 | Slight Delay | 20 | Approval | Structure Done | Structure | 60% | Partial | 18 | 25 | Packaging Line 1 | 0 | 94% | Tiles | 200 | 215 | a | 60% | Approval | Design change | Fast-track | Passed | Rework | 2025-02-05 | No | Medium | 55 | 0.55 | 2025-03-31 | Waste water
9 | Bus Stop Shelter | MetroInfra | Transport | Completed | Zone B | 2024-11-01 | 2025-01-31 | On Track | 0 | No | Completed | Paving | 40% | Complete | 50 | 55 | Packaging Line 2 | 0 | 89% | Steel | 30 | 29 | a | 100% | None | None | NA | Passed | Nil | 2025-01-28 | No | High | 100 | 1 | 2025-01-31 | Recyclable
10 | Garden Development | GreenScape | Parks | In Progress | Zone C | 2025-02-01 | 2025-05-31 | On Track | 0 | No | Plantation Started | Laying | 70% | Complete | 15 | 15 | Conveyor Belt | 0 | 75% | Plants | 500 | 480 | a | 65% | Weather | None | Shade nets | Passed | Nil | 2025-03-25 | No | High | 68 | 0.68 | 2025-06-10 | Water saving
11 | Road Widening | ABC Infra | Roads | In Progress | Zone D | 2025-01-15 | 2025-08-31 | Slight Delay | 5 | Utility | Demolition Done | Electrical | 65% | Partial | 50 | 55 | CIP Unit | 0 | 66% | Soil | 1200 | 1180 | a | 55% | Utilities | Cable shift | Coordination | Passed | Nil | 2025-04-02 | No | High | 52 | 0.52 | 2025-09-15 | Dust control
12 | Culvert Repair | XYZ Constructions | Roads | Completed | Zone E | 2024-10-01 | 2024-12-31 | On Track | 0 | No | Completed | Wiring | 30% | Complete | 35 | 35 | Refrigeration System | 0 | 92% | RCC | 90 | 88 | a | 100% | None | None | NA | Passed | Nil | 2024-12-20 | No | High | 100 | 1 | 2024-12-31 | Silt mgmt
13 | Electrical Substation | PowerGrid | Electrical | In Progress | Zone A | 2025-03-01 | 2025-07-31 | On Track | 0 | No | Equipment Installed | Wall | 50% | Partial | 22 | 25 | Generator Set | 0 | 60% | Panels | 10 | 11 | a | 60% | Supply | Panel delay | Air freight | Passed | Nil | 2025-04-12 | No | High | 62 | 0.62 | 2025-08-10 | Energy norms
14 | Sewer Network | DrainTech | Water Supply | Delayed | Zone F | 2024-12-15 | 2025-04-30 | Slight Delay | 30 | Labor | Laying Started | Tiles | 70% | Partial | 26 | 40 | Water Treatment Unit | 0 | 73% | Pipes | 700 | 730 | a | 45% | Labor | Shortage | Local hire | Passed | Minor | 2025-03-18 | Minor | Medium | 43 | 0.43 | 2025-05-31 | Waste mgmt
15 | Community Hall | BuildWell Ltd | Buildings | In Progress | Zone B | 2025-02-01 | 2025-10-31 | On Track | 0 | No | Foundation Done | Finishing | 40% | Complete | 35 | 35 | Air Compressor | 0 | 86% | Cement | 300 | 295 | a | 25% | Funding | None | Staged work | Passed | Nil | 2025-04-05 | No | High | 25 | 0.25 | 2025-11-15 | Green norms